# Phase 1 — Foundation: Detailed Work & Workflow (per Pod)

Multi-tenant University AI SaaS — Frontend / Backend / AI-Services / Infra

Goal: Every pillar (Frontend, Backend, AI-Services) boots, is containerized, and can talk to its neighbor with no real features yet. By end of phase, "docker-compose up" brings the whole system online and a health request flows Frontend -> Backend -> AI-Services -> DB/Vector-DB.

Suggested duration: 5 working days (1 sprint).

# 0. Pod Composition & Focus This Phase

| Pod | Phase-1 Focus | Devs |
| --- | --- | --- |
| Pod 1 | Frontend shell + auth UI | 2-3 |
| Pod 2 | Backend core (tenancy + security) | 2-3 |
| Pod 3 | AI-Services scaffold + serving | 2-3 |
| Pod 4 | Infra: Docker, K8s, Terraform, CI | 2-3 |
| Lead | Cross-pillar API contracts, standards, integration | 1 |

# 1. Dependency & Sequence Map

Day 0 (Lead) --> Repo + monorepo skeleton + API contracts agreed
        |
   +----+--------------------+--------------------+--------------------+
   v                         v                    v                    v
Pod 4 (Infra)          Pod 2 (Backend)      Pod 3 (AI-svc)       Pod 1 (Frontend)
docker-compose+CI      config/db/core       scaffold+health      shell+auth UI
(everyone depends      (needs DB from       (no external dep)    (needs backend
 on this FIRST)         Pod 4 compose)                            health contract)
   |                         |                    |                    |
   +--------> INTEGRATION CHECKPOINT (Day 4): health call traverses all pillars <--+

Critical path: Lead contracts (Day 0-1) -> Pod 4 docker-compose (Day 1) -> all other pods build against it. Pod 4 MUST deliver compose + shared .env.example by end of Day 1 or other pods are blocked.

# 2. Lead — Day 0/1 (must finish first)

Create monorepo: empty frontend/ backend/ ai-services/ deploy/ docs/ scripts/ + README, .gitignore (ignore node_modules, .env, model weights), docker-compose.yml placeholder.

Branch & PR strategy: main (protected) -> develop -> feat/<pod>-<task>. PRs need 1 review by incoming Primary + green CI.

Agree 3 API contracts in docs/contracts/: Frontend<->Backend (base URL, /api/health shape, Authorization Bearer, tenant resolution); Backend<->AI (internal URL, /health + /v1/echo); standard response envelope {data, error, request_id}.

Coding standards: ESLint/Prettier (frontend), ruff/black (Python) wired into CI.

Post Definition of Done checklist for the whole team.

Lead deliverable: repo scaffold + docs/contracts/*.md + DoD merged to develop by end of Day 1.

# 3. Pod 4 — Infrastructure (highest priority, unblocks others)

| Day | Work | Deliverable |
| --- | --- | --- |
| 1 | docker-compose.yml with 5 services: frontend, backend, ai-services, postgres, vector-db (pgvector/Qdrant); shared network + .env.example | docker-compose up boots DB + Vector DB; placeholder app containers |
| 1-2 | 3 Dockerfiles in deploy/docker/ (frontend, backend, ai) - multi-stage dev+prod | Each pillar builds into an image |
| 2-3 | CI pipeline (lint+build+test stub) on every PR to develop | Green CI; PRs blocked if red |
| 3-4 | Base Terraform in deploy/terraform/ (VPC, Postgres, object storage, vector DB, GPU node-pool) - plan only | terraform plan runs clean |
| 4-5 | Base K8s manifests in deploy/k8s/ (namespaces, deployments, services, ingress) - not deployed | kubectl --dry-run validates |

DoD: any dev runs docker-compose up and gets all 5 services healthy; CI runs on PRs; Terraform/K8s skeletons reviewed.

# 4. Pod 2 — Backend Core (tenancy + security)

| Day | Work | Deliverable |
| --- | --- | --- |
| 1 | config.py (settings from .env) + database.py (SQLAlchemy engine + session) | App reads env; DB session opens against compose Postgres |
| 1-2 | core/tenancy/ middleware resolves tenant_id (subdomain/header) into request context + scoping helper | Every request has tenant_id (stub tenant) |
| 2 | core/security/ JWT verify dependency + RBAC role skeleton (no real login) | Protected route rejects missing/invalid token |
| 2-3 | main.py bootstrap + register routers + /api/health (checks DB) | GET /api/health returns agreed envelope |
| 3 | clients/ai_client.py thin HTTP client calling AI-services /health + /v1/echo | Backend reaches AI-services |
| 3-4 | Alembic setup + empty initial migration (no business tables) | alembic upgrade head runs in compose |
| 4 | Wire /api/health to also report AI-services reachability | Health OK only when DB + AI-svc reachable |

DoD: /api/health returns OK, validates a JWT on a protected stub, resolves tenant context, confirms AI-services connectivity.

# 5. Pod 3 — AI-Services Scaffold + Serving

| Day | Work | Deliverable |
| --- | --- | --- |
| 1 | Scaffold ai-services app with /health | Service boots in compose |
| 1-2 | serving/llm_server/ config for self-hosted model (vLLM/Ollama) in mock/CPU mode (no GPU dependency) | LLM serve config present; mock mode works on CPU |
| 2 | serving/embeddings/ stub + model_registry/models.yaml (names/versions/endpoints; NO weights in repo) | Registry validated; scripts/model-download placeholder |
| 2-3 | serving/router/ skeleton (self-hosted vs OpenAI interface; returns mock) | Router interface callable |
| 3 | /v1/echo stub endpoint per Backend<->AI contract | Backend ai_client gets valid response |
| 3-4 | Folder scaffolds: rag/ingestion, rag/retrieval, rag/pipeline, rag/guardrails, workers/ (empty + READMEs) | Structure ready for Phase 2 |

DoD: AI-services boots in compose, /health + /v1/echo respond per contract, model registry present, weights excluded from git.

FLAG TO MANAGER: To avoid GPU dependency in Phase 1, the LLM runs in MOCK/CPU mode. Real model serving is deferred to Phase 2/3 once GPU infra (Pod 4 Terraform) is provisioned.

# 6. Pod 1 — Frontend Shell + Auth UI

| Day | Work | Deliverable |
| --- | --- | --- |
| 1 | Bootstrap React app (app/ routing, providers, layout); env-based backend URL | App runs in compose, renders shell |
| 1-2 | lib/ API client (reads backend URL, attaches Authorization header, parses envelope) | Client wired to backend |
| 2 | auth/ login screen + SSO button (UI only) + JWT/session storage scaffolding | Login page renders; token storage stubbed |
| 2-3 | Role-aware routing: empty student/, professor/, admin/, tenant-admin/ shells | Navigating by role shows correct shell |
| 3 | System status page calling /api/health showing backend + AI-svc status | Frontend -> Backend -> AI health visible in UI |
| 3-4 | components/ui/ base design-system primitives + theme | Shared UI kit ready for Phase 2 |

DoD: frontend boots in compose, shows role-based shell, status page proves full chain Frontend->Backend->AI reachable.

# 7. Day-by-Day Gantt (X = active, * = key event)

| Workstream | D1 | D2 | D3 | D4 | D5 |
| --- | --- | --- | --- | --- | --- |
| Lead: repo + contracts | X |  |  |  | * |
| Pod 4: docker-compose + .env | X | X |  |  |  |
| Pod 4: Dockerfiles + CI | X | X | X |  |  |
| Pod 4: Terraform + K8s |  |  | X | X | X |
| Pod 2: config/db/core | X | X |  |  |  |
| Pod 2: security + health + ai_client |  | X | X | X |  |
| Pod 2: Alembic migration |  |  | X | X |  |
| Pod 3: scaffold + health | X | X |  |  |  |
| Pod 3: serving + registry + router |  | X | X | X |  |
| Pod 3: /v1/echo + rag scaffolds |  |  | X | X |  |
| Pod 1: app shell + API client | X | X |  |  |  |
| Pod 1: auth UI + role shells |  | X | X |  |  |
| Pod 1: status page + UI kit |  |  | X | X |  |
| INTEGRATION CHECKPOINT |  |  |  | * |  |
| Hardening + Demo + Retro |  |  |  |  | * |

# 8. Daily Workflow

Day 0-1 Setup & contracts: Lead lands repo + contracts; Pod 4 lands compose + .env.example. Other pods scaffold against compose stubs.

Day 2 Parallel build: each pod builds its skeleton against agreed contracts; mock the neighbor if not ready. No pod waits on another internal code, only on the contract.

Day 3 First wiring: Backend<->AI /v1/echo; Frontend<->Backend /api/health. Open integration PRs.

Day 4 Integration checkpoint (key event): whole team runs docker-compose up; verify one health request traverses Frontend -> Backend -> AI -> DB/Vector-DB. Fix breakages together.

Day 5 Hardening + demo: green CI, README updated, each pod demos; Lead confirms exit criteria; retro + plan Phase-2 rotation.

Rituals: 15-min daily standup (shipped/blocked/next); contract changes go through the Lead; PRs reviewed by the incoming Primary of that pillar (knowledge rotates into next phase).

# 9. Phase-1 Exit Criteria (Demo Gate Checklist)

[ ]  docker-compose up boots all 5 services healthy.

[ ]  Frontend renders role-based shells + login/SSO UI (no real auth yet).

[ ]  GET /api/health returns OK, validates JWT on a protected stub, resolves tenant_id.

[ ]  Backend reaches AI-services (/v1/echo); AI-services serves in mock mode.

[ ]  A single health request visibly traverses Frontend -> Backend -> AI -> DB/Vector-DB.

[ ]  CI (lint + build + test stub) green on develop; Terraform plan and K8s --dry-run validate.

[ ]  docs/contracts/ complete; README updated; every pod has demoed.

# 10. Decisions to Confirm Before Kickoff

Vector DB choice for compose: pgvector (simplest) vs Qdrant (scales better)?

Confirm LLM mock mode in Phase 1 is acceptable (real GPU serving deferred to Phase 2)?